## Artistory
	Product Backlog items Total	1st Sprint backlog items	In design	In development	Done
Start	5	20	4	3	0
Mon 14th	5	10	5	4	1
Tue 15th	5	9	3	3	5
Wed 16th	5	7	5	1	7
Thurs 17th	5	7	2	2	9
Fri 18th		5	2	2	11
Mon 22nd		4	2	2	12
Tues 23rd		3	0	5	12
Wedn 24th		2	0	2	16

## Artistory_sprint1
SPRINT 1	List of tasks	Status	Number of hours foreseen	Number of hours done -Monday	Total number of hours		Progress-Monday	Number of hours done-Tuesday	Progress-Tuesday	Number of hours done-Wednesday	Progress-Wednesay	Number of hours done-Thursday	Progress-Thursday	Number of hours done-Friday
	1.Create login/session table in DB		2	2			100,00%		0,00%		#DIV/0!		#DIV/0!
	1. Create login/session form. (HTML/CSS/JS)		2
	1.Create REST API for login. (PHP)		4
	1.Connect login form to REST API. (JS/AJAX)		2
	2. 2.Session management REST API (PHP)		4
	3.a. Create profile table in DB (SQL)		2
	3.b. Create profile form for creating and editing profiles. (HTML/CSS/JS)		4
	3.c. Create REST API for profile data . (PHP)		3
	3.d. Connect profile form to REST API. (JS/AJAX)		3
	3.e. Add session management.		2
	4.View profile (HTML/CSS/JS/AJAX)		10
	5.a. Create database table for filenames on server.		2
	5.b. Create the form for uploading files.		2
	5.c. Create the REST API to accept/serve uploaded files.		6
	7.Create templates		10
	8.a. Create form for editing metadata of files that were uploaded.		5
	11.Main page/home page (HTML/CSS/JS)		10
	12.a. Create icons and buttons.		1
	12.b. Create the REST API for artwork likes to artwork table.		5
	13 Database setup		1
			80